## Slide 1
Technical Assistance for Development of End-Of-Waste Concept in Türkiye
TR2018 ESOP MI A2.05 / SER / 31
June 15, 2023
Ankara
Opening Event Project Introductory Presentation Elina Velinova STOYANOVA-LAZAROVA
Team Leader

## Slide 2
Overall Objective
To reduce depletion of natural resources used in production and amount of waste generated by promoting the usage of secondary raw materials and enhancing market for high quality recyclables, which ultimately contribute to the sustainable development of the country
Project Purpose
To develop technical and institutional capacity for identification and effective implementation of End-of-Waste criteria for specific waste streams in Türkiye in line with the Waste Framework Directive (2008/98/EC) and the Directive (2018/851).
Result 1
Result 2
Result 3
Current situation is analysed for potential of ten waste streams as secondary raw materials in Turkish context within the perspective of End-of-Waste concept
A comprehensive national strategy and technical capacity is developed for implementation of End-of-Waste criteria for different waste streams.
Capacity of competent authorities and relevant sectors on waste as a resource concept and on implementation of End-of-Waste criteria is improved in Türkiye.
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 3
Component 1
Analysis of candidate waste streams for End-of-Waste criteria in Türkiye
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 4
Copper Scrap
Metal (Iron, steel and aluminium) Scrap
Glass Cullet
Waste Paper
Biodegradable Waste
Waste Plastic
Waste Textiles
Construction Aggregates
Waste Tyres
Refuse Derived Fuel (RDF)
Activity 1.1 Analysis of Waste Streams in Türkiye
Current situation in Türkiye will be assessed including collection, current processes applied (recycling, recovery…etc.), uses of recycled or recovered materials, available standards or specifications, market for trade (internal and abroad), demanding sectors
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 5
Sub-Activity 1.1.1
Guideline on clarification and harmonisation of waste related definitions
Sub-Activity 1.1.2
Sub-Activity 1.1.3
Sub-Activity 1.1.4
Activity 1.1 Analysis of Waste Streams in Türkiye
outputs
Questionnaire forms on data collection
outputs
outputs
outputs
Technical site visits
Report on analysis of waste streams in Türkiye
100 filled questionnaires
Company Visits Reports
Presentation of main findings for each waste stream
Technical Assistance for Development of End-Of-Waste Concept in Türkiye
Notes: Political commitment is crucial. Uncertainties for adoption of new Laws (i.e. draft Framework Law on waste, Draft Law on Ecological control, Draft Law on chemical safety, etc.) and the possible changes in the future could potentially affect the activities related to the drafting of new legislation
Mutual trust and respect is a crucial condition for the success of project activities

## Slide 6
Guidance report on clarification and harmonisation of waste related definitions and concepts
Analysis of both the EU and Turkish legislation - review amended EU Waste Framework Directive, definitions used for statistical purposes by Eurostat and the Organisation for Economic Cooperation and Development (OECD) and Turkish waste related legislation including recent By-Law on Zero Waste, By-Law on Waste Management
Harmonisation of definitions and concepts of waste, municipal waste, hazardous/non-hazardous waste, pre-treatment, prevention, re-use, preparation for re-use, recycling, recovery, disposal, production residue, secondary raw material, alternative fuel, alternative raw material, industrial symbiosis, by-product, end-of waste.
Sub-Activity 1.1.1
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 7
Review of the existing databases such as Waste Declaration System (TABS), Mobile Waste Tracking System (MoTAT), Mass Balance System (KDS), Packaging Information System (ABS), and inventories from other studies, TurkStat database, Industry Databases, data from national and international reports on the field, other relevant studies
Develop stakeholder matrix
Data collection on waste streams through questionnaires, adapted for each industry and for each type of materials
Data and information to be compiled for each of 10 waste streams
Sub-Activity 1.1.2
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 8
Technical site visits
For each waste stream 3 industries will be selected, in total 30 company visits will be conducted
Aim of the company visits is to support data collection and track the flow of waste streams on site
30 Company Visits Reports
One comprehensive report based on 30 company visits
Sub-Activity 1.1.3
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 9
Comprehensive report on the analysis of selected 10 waste streams in Türkiye, based on Results of the activity 1.1.2 and 1.1.3
Environmental and human health impacts, economic and market impacts and social impacts associated with each waste stream will be assessed briefly for the current situation
Prepare a comparison base for impact assessments studies to be conducted in the second component of the project and other future impact assessment studies necessary to introduce end-of-waste criteria for a specific waste stream
Sub-Activity 1.1.4
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 10
Activity 1.2 Benchmark analysis on related End-of-Waste legislation and practices between Türkiye and the EU
First section
  Repository document for all adopted national and EU level end-of-waste, alternative raw material and by-product criteria in the EU and compare 2 selected EU countries with current situation in Türkiye in terms of legislation including strategy papers, administrative procedures, plans, laws, acts and regulations.
Second section
  Member States' practices regarding implementation and verification of provisions on end-of-waste criteria and by-product conditions
2 section report on benchmark analysis
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 11
Task
2.1
Component 2
Development of national strategy and technical capacity about implementation of End-of-Waste criteria in Türkiye
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 12
Sub-Activity 2.1.1
Impact assessment studies on End-of-Waste Criteria for iron, steel and aluminium scrap, glass cullet and copper scrap according to Turkish context
Sub-Activity 2.1.2
Sub-Activity 2.1.3
Activity 2.1 Preparation of draft Technical Regulations
outputs
Nine workshops on Impact assessment studies
Three separate workshops for each of the waste streams (iron, steel and aluminium scrap, glass cullet and copper scrap)
outputs
outputs
Draft Technical Regulations
environmental and human health impact assessment
economic and market impact assessment
legislative and social impact assessments
3 Draft Technical Regulations on establishing criteria determining when certain types of metal (iron, steel and aluminium) scrap, glass cullet and copper scrap cease to be waste
Technical Assistance for Development of End-Of-Waste Concept in Türkiye
Draft Regulation on general principles of end-of waste criteria
Notes: Political commitment is crucial. Uncertainties for adoption of new Laws (i.e. draft Framework Law on waste, Draft Law on Ecological control, Draft Law on chemical safety, etc.) and the possible changes in the future could potentially affect the activities related to the drafting of new legislation
Mutual trust and respect is a crucial condition for the success of project activities

## Slide 13
End-of-waste criteria are not compulsory, choice / benefit whether to seek end-of-waste certification or continue to manage the material as waste
Waste Framework Directive 2008/98/EC
Council Regulation (EU) No 333/2011 on determining the criteria for end of waste status regarding iron, steel and aluminium scrap
Council Regulation (EU) No. 1179/2012 on determining the criteria for end of waste status in relation to glass gullet
Council Regulation (EU) No. 715/2013 on determining criteria for end of waste status regarding copper scrap
Activity 2.1 Preparation of draft Technical Regulations
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 14
Report of Impact assessment studies on End-of-Waste Criteria for iron, steel and aluminium scrap, glass cullet and copper scrap according to Turkish context as described in the section 1.5 of the JRC’s End-of-Waste Criteria report
  comparison of impacts with “end-of-waste criteria scenario” with “no action or business as usual scenario”
  Economic and market impact assessment
  Legislative impact assessment
  Social impact assessment
  Previous studies on impact assessment studies from the EU member states or JRC will be used as guidance
  The results of the workshops described in Activity 2.1.2 will be integrated into this report
Activity 2.1 Preparation of draft Technical Regulations
Sub-Activity 2.1.1

## Slide 15
Nine workshops on Impact Assessment Studies
For each of the waste streams (iron, steel and aluminium scrap, glass cullet and copper scrap, three separate workshops will be organised
First workshop about environmental and human health impact assessment
Second workshop about economic and market impact assessment
Third workshop will cover legislative and social impact assessments together
Activity reports of workshops
Activity 2.1 Preparation of draft Technical Regulations
Sub-Activity 2.1.2
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 16
Waste Framework Directive 2008/98/EC
Draft Regulation on general principles of end-of waste criteria
Development of 3 Draft Technical Regulations
Council Regulation (EU) No 333/2011 on determining the criteria for end of waste status regarding iron, steel and aluminium scrap
Council Regulation (EU) No. 1179/2012 on determining the criteria for end of waste status in relation to glass gullet
Council Regulation (EU) No. 715/2013 on determining criteria for end of waste status regarding copper scrap
Activity 2.1 Preparation of draft Technical Regulations
Sub-Activity 2.1.3
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 17
Waste input material for the recovery operation is permissible.
The treatment processes and techniques are allowed.
The quality criteria applied to the end-of-waste materials are in line with the applicable product standards, including limit values for pollutants where necessary
Requirements are set for management systems to demonstrate compliance with the end-of-waste criteria including for quality control and self-monitoring, and accreditation.
Requirement for a statement of conformity.
Activity 2.1 Preparation of draft Technical Regulations
Sub-Activity 2.1.3
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 18
metal (iron, steel and aluminium) scrap
copper scrap
glass cullet
5th workshop
Discuss both Draft Regulation on determining the criteria for end of waste status regarding iron, steel and aluminium scrap and guidelines
Discuss both Draft Regulation on determining the criteria for end of waste status in relation to glass gullet and guideline
Discuss both Draft Regulation criteria for end of waste status regarding copper scrap and guideline
Discuss regulations and guideline for case by case determination of end-of-waste status independent from the waste stream
Activity 2.2 Workshops to evaluate regulations and guidelines prepared within the project
Five Evaluation Workshops
textile
Discuss both Draft Regulation criteria for end of waste status regarding textile and guideline
(online workshop)

## Slide 19
Review the amendments in the EU Waste Framework Directive 2008/98/EC and other related EU legislation
Report on recommendations on possible changes and amendments after adopting the end-of-waste criteria to the relevant Turkish waste legislation
Report about recommendations on revision of National Regulations on Waste
Roadmap/ National Strategy document of Türkiye for introduction and implementation of end-of-waste criteria for different waste streams in Türkiye
Activity 2.3 Revision of National Regulations and Preparation of Roadmap on implementation of end-of-waste criteria for different waste streams

## Slide 20
Guidance for iron, steel and aluminium scrap
Guidance for copper scrap
Guidance for glass cullet
Guidance for construction aggregates
General Guidance for end-of-waste
1
1
2
3
4
Guidance for biodegradable waste (compost and digestate)
5
Guidance for textile
5
6
7
Activity 2.4 Guidelines on Implementation of End-of-waste in Türkiye
Notes: Political commitment is crucial. Uncertainties for adoption of new Laws (i.e. draft Framework Law on waste, Draft Law on Ecological control, Draft Law on chemical safety, etc.) and the possible changes in the future could potentially affect the activities related to the drafting of new legislation
Mutual trust and respect is a crucial condition for the success of project activities

## Slide 21
The Make it Work initiative (MiW) is a joint effort with the European Union Network for the Implementation and Enforcement of Environmental Law (IMPEL)
Tool developed by IMPEL is ‘Making the Circular Economy Work – Guidance for regulators’
Eurostat Guidance on municipal waste data collection, JRC Guidance for separate collection of municipal waste, EU reference model harmonising separate waste collection systems form 2020
EU Science Hub (RMIS) policies and definitions (example secondary raw material)
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 22
Technical Assistance for Development of End-Of-Waste Concept in Türkiye
https://susproc.jrc.ec.europa.eu/susproc_home
Less waste, more value.
List of publications of JRC research on waste
Webpage on Best Environmental Management Practice
Webpage with additional background information on Best Environmental Management Practice
Webpage on Green Best Practice Community

## Slide 23
Creator: Attard Bason Marie Claire at ERA https://era.org.mt/topic/end-of-waste-criteria/
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 24
Sorting of mixed municipal waste
  Production and market for RDF?
RDF Power Plant Peute 100 MWel – 700,000 t RDF/ a
Cement Plant
Paper factory Lenzing
RDF steam plant
Composting
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 25
4
2.1
Quality management system (ISO 9000 series) / environmental management system (ISO 14000 series), or EMAS includes a set of documented procedures regarding:
1) control of the acceptance of waste used as an input fraction;
2) monitoring of processes and technologies (recovery operations);
3) monitoring the quality of glass gullet / scrap metal obtained as a result recovery operations (including sampling and analysis);
4) customer reviews regarding compliance of broken glass/ scrap metal with quality standards;
5) keeping records of monitoring results, which is carried out in accordance with items (1) to (3);
6) effectiveness of radiation monitoring (for scrap metal);
7) analysis and measures to improve the management system;
8) staff training. The management system should also define the specific monitoring requirements outlined for each criterion.
Technical Assistance for Development of End-Of-Waste Concept in Türkiye
Notes: Political commitment is crucial. Uncertainties for adoption of new Laws (i.e. draft Framework Law on waste, Draft Law on Ecological control, Draft Law on chemical safety, etc.) and the possible changes in the future could potentially affect the activities related to the drafting of new legislation
Mutual trust and respect is a crucial condition for the success of project activities

## Slide 26
Task
2.1
Component 3
Capacity development of competent authorities and relevant target groups in terms of End-of-Waste implementation in Türkiye
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 27
First Training 1
BRIF
Second training 2
Third Training 3
For the competent authorities in Türkiye to get familiar with the end-of-waste framework including legislation and practices in the EU in the context of assessment, inspection and monitoring of the end-of-waste
For the representatives of the industrial sectors from stakeholders and target groups to introduce end-of-waste framework and details of the guidelines prepared in the activity 2.3 -metal (iron, steel, aluminium) and copper sector
For the representatives of the industrial sectors from stakeholders and target groups for glass sector and any other sector interested in end-of-waste in Türkiye
Activity 3.1 Training Programs
Notes: Political commitment is crucial. Uncertainties for adoption of new Laws (i.e. draft Framework Law on waste, Draft Law on Ecological control, Draft Law on chemical safety, etc.) and the possible changes in the future could potentially affect the activities related to the drafting of new legislation
Mutual trust and respect is a crucial condition for the success of project activities

## Slide 28
Activity 3.2 Performing Study Visit
1 study visit which covers 2 EU countries
EU Country 1
EU Country 2

## Slide 29
Task
2.1
Component 4
Publicity Activities
Technical Assistance for Development of End-Of-Waste Concept in Türkiye

## Slide 30
Communication Strategy and Action Plan
Activity 4.1
Project website and social media accounts
Activity 4.3
Closing meeting
Activity 4.5
Activity 4.2
Opening Meeting
Activity 4.4
Preparation of project short video and other visibility materials
Activities

## Slide 31
Project website and social media accounts
All social media account names taken on June 8th. The website is under construction.
@atiksonu_endofwaste
@atiksonu_eow
www.facebook.com/atiksonu.endofwaste
www.linkedin.com/company/atiksonu-endofwaste
Activity 4.3: Project website and social media accounts

## Slide 32
Technical Assistance for Development of End-Of-Waste Concept in Türkiye
  Teşekkürler!